## Sheet1
Milestones List
Major Milestones | Explanations
Clean up and organize data | Data must be collected and organized in order for me to properly use it
Analyze Data and create charts to find trends | Data must be analyzed and looked into in order to find relationships between the variables
Use mapbox to create heatmap | The software mapbox will be used to create a heatmap with relative ease once I understand the software
Add other possible ideas | More advanced ideas can be added to this project, but only if it is deemed necessary.
It is outlined in my design diagram
Timeline
Date Completion | Task
2024-01-05 | Find appropriate data
2024-01-06 | Download and get this data in .csv format
2024-01-07 | Combine data if necessary from different sources
2024-01-08 | Clean up data, only keep what is necessary
2024-01-09 | Remove null values in data
2024-01-10 | Put all this data into an SQL database or keep using excel .csv
2024-02-10 | Create quick charts of this data to help find trends
2024-02-20 | Analyze different variables such as Type, Location, Time, etc.
2024-02-20 | Look for trends in the data
2024-03-02 | Learn best techniques to create maps on mapbox software
2024-03-10 | Use mapbox to create heatmap
2024-03-21 | Create other useful visuals
2024-04-02 | Customize this heatmap and make it easily readable for the audience
2024-04-05 | Other Possibilities: Interactive dashboard, predictive modeling, etc.
For Task Completion, All tasks start at 1/1/2023, once we are back from winter break and begin to work on projects
Effort Matrix
Person Responsible | Task | Hours
Ted Cordonnier | Find appropriate data | 4
Ted Cordonnier | Download and get this data in .csv format | 1
Ted Cordonnier | Combine data if necessary from different sources | 2
Ted Cordonnier | Clean up data, only keep what is necessary | 4
Ted Cordonnier | Remove null values in data | 1
Ted Cordonnier | Put all this data into an SQL database or keep using excel .csv | 2
Ted Cordonnier | Create quick charts of this data to help find trends | 2
Ted Cordonnier | Analyze different variables such as Type, Location, Time, etc. | 8
Ted Cordonnier | Look for trends in the data | 4
Ted Cordonnier | Learn best techniques to create maps on mapbox software | 3
Ted Cordonnier | Use mapbox to create heatmap | 6
Ted Cordonnier | Create other useful visuals | 6
Ted Cordonnier | Customize this heatmap and make it easily readable for the audience | 2
Ted Cordonnier | Other Possibilities: Interactive dashboard, predictive modeling, etc. | 0
Total Hours | At Least 45 Hours of Effort per Semester | 45